## Relationships 1.1
Relationships
Sustained relationships built on respect, trust and integrity are foundational to engagement with Aboriginal and Torres Strait Islander Peoples. Strong relationships between Aboriginal and Torres Strait Islander Peoples and the AISSA are pivotal to being brave and advocating for truth telling and equity, as individuals and as an organisation. | [5 empty] | Review, Discuss, Act |  |  |  | Ongoing
Action | Responsibility | Timeline | Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Establish and maintain mutually beneficial relationships with Aboriginal and Torres Strait Islander stakeholders and organisations. | Senior Reconciliation Consultant | March 2023, 2024, 2025 | Meet with local Aboriginal and Torres Strait Islander stakeholders and organisations to continuously improve guiding principles for engagement. | Review, Discuss, Act Mar: 2024
| Senior Reconciliation Consultant | June 2024 | Review, update and implement an engagement plan to work with Aboriginal and Torres Strait Islander stakeholders.
| Senior Reconciliation Consultant | September 2024 | Establish and maintain 3 formal two-way partnerships with Aboriginal and Torres Strait Islander communities or organisations.
| Senior Reconciliation Consultant | December 2023, 2024, 2025 | Engage in ongoing partnerships with Reconciliation SA, Culture College, and Uncle John Lochowiak.
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Populate the spreadsheet by inserting your text in the comment box. Reply: 2023 First meeting between AM, KM & SB with Aunty Elaine to plan the opportunities for the year ahead. Reply: 2024 KM met with Aunty Elaine to establish and plan the year ahead. Reply: 2023 KM met with Uncle John to plan the opportunities for the year ahead. Reply: 2024 KM met with Uncle John to plan the opportunities for the year ahead. Reply: 2023 KM met with Justin Porter from Culture College to map out immersion trip pathway. Reply: 2024 KM met with Justin Porter from Culture College to map out immersion trip pathway.
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 AISSA Stakeholders Morning Tea. AISSA introduced to Robert Taylor. Reply: 2023 KM met Simon McCormick from Australian Together to continue working partnership.
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 KM met with Justin Porter from Culture College to map out immersion trip pathway. 2024 KM met with Justin Porter from Culture College to map out immersion trip pathway.
Note on K4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 KM met Jade Brook from Australians Together to establish ongoing partnership. Reply: 2023 KM met Simon McCormick from Australian Together to continue working partnership.
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 KM introduced Jade Brook to SB to develop further the relationship. Reply: Aunty Elaine through the Creating Culturally Safe Schools PL shared positive engagement strategies and protocols with AISSA staff and staff from member schools.
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KS met with Jade Brook from Australians Together re way to support Schools with their Ack of Country from a Christian perspective. Reply: 2024 KS met with Aunty Elaine.
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AD/LS met with Exec Dire of Australians Together (Liam Glover)
Note on N5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 KM and SB reviewed and updated Stakeholder List. Reply: 2024 Engagement plan for the AISSA PL plan for 2025, and foreword planning key events for 2025.
Note on O5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 KM/SB shared the Stakeholder list with the RWG as a tabled agenda item.
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 KM met with Justin Porter from Culture College to map out immersion trip pathway. 2024 KM met with Justin Porter from Culture College to map out immersion trip pathway. Reply: 2023 KM met with Simon McCormick from Australian Together to map out immersion trip pathway. 2024 KM met with Simon McCormick from Australian Together to map out immersion trip pathway. Reply: 2023 KM engage partnership with Ochre Dawn Creative Industries for Stretch RAP graphics and working partnership. Reply: 2024 KM engage partnership with Ochre Dawn Creative Industries and ongoing working partnership. Reply: 2023 KM met with Natalie Gentle Reconciliation SA re ongoing partnership. 2024 KM met with Natalie Gentle Reconciliation SA re ongoing partnership.
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Culture College Immersion Trip. 2024 Jade Brook future PL at AISSA.
Note on N6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Culture College visit AISSA staff meeting to share culture. Reply: 2024 AD/KS meet with CEO Australians Together to begin a conversation.
Note on M7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 KM/SB visit Ngutu College, Principal Andrew Plastow reciprocates to share learning at AISSA PL for schools. Reply: 2024 KS meet with Aunty Elaine for a coffee conversation.
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 & 2025. These partnerships were established through meetings with and an ongoing engagement plan throughout the year.
Note on L8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KM met with Rec SA: Natalie and Kirsty Reply: KM met with Uncle John.
Note on N8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 KS/LP/LC attend First Nations Business Showcase at the Entertainment Centre.
Note on O8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 Evaluative meetings were held to review our partnership and strategize for future opportunities. Reply: 2024 Culture College. Djapirri has accepted invitation to spend time at the AISSA on 31 October from 2.00pm at Secondary/Combined Principal’s meeting. Reply: 2024 Culture College via a Teams information meeting for interested people to attend the 2025 Immersion Trip. Reply: 2024 KS coffee conversation with Uncle John.

## Relationships 1.2
Relationships
Sustained relationships built on respect, trust and integrity are foundational to engagement with Aboriginal and Torres Strait Islander Peoples. Strong relationships between Aboriginal and Torres Strait Islander Peoples and the AISSA are pivotal to being brave and advocating for truth telling and equity, as individuals and as an organisation. | [5 empty] | Review, Discuss, Act |  |  |  | Ongoing
Action | Responsibility | Timeline | Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
2. Build relationships through celebrating National Reconciliation Week (NRW). | Senior Reconciliation Consultant and RWG Communication Consultant | April 2023, 2024, 2025 | Circulate Reconciliation Australia’s NRW resources and reconciliation materials to all staff.
| Senior Reconciliation Consultant | April 2024, 2025, 2026 | Invite member schools to participate in the Reconciliaiton SA NRW Breakfast event.
| Senior Reconciliation Consultant | March 2024, 2025, 2026 | Support member schools to plan and resource for NRW events through newsletters and professional learning opportunities.
| Senior Reconciliation Consultant | May 2023, 2024, 2025 | Provide a professional learning opportunity in partn ership with a Kaurna Elder leading up to NRW, with intentional connection to NRW for our member schools.
| Senior Reconciliation Consultant | August 2023, 2024, 2025 | Encourage member schools to share their NRW activities via an allocated section on the AISSA website.
| Chief Executive and RWG Event Coordinators | 27 May to 3 June 2023, 2024, 2025 | RAP Working Group members to participate in at least 5 external NRW events.
| Chief Executive and RWG Event Coordinators | 27 May to 3 June 2023, 2024, 2025 | Encourage and support staff and senior leaders to participate in 3 external events to recognise and celebrate NRW, including the Reconciliation SA NRW Breakfast.
| RWG Event Coordinators | 27 May to 3 June 2023, 2024, 2025 | Organise 1 internal organisational NRW event each year.
| RWG Event Coordinators | April 2023, 2024, 2025 | Register our NRW events on Reconciliation Australia's NRW website.
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 and 2024 KM shared to all staff.
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 Shared to all staff by Senior Reconciliation Consultant.
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 Invited specific schools to attend the breakfast and we notified AISSA member schools. 2024 Notified member schools of the event. Reply: 2025 Notified member schools of the event
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2025 notified member schools of the event
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 PL: Creating Culturally Safe Classrooms and Schools, leading into NRW. Reply: 2024 Newsletter from KM circulated to member schools sharing plans and resources for NRW. Reply: 2025 Email with NRW specific events and resources shared with member schools.
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2025 Your RAP Journey - next brave steps. 1 of 2 workshops held at AISSA. Uncle John shared a Welcome to Country, Smoking Ceremony and why reconciliation in schools is important.
Note on I7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 AISSA PL, workshop 1 of a 3 part series with Uncle John with intentional connection to NRW
Note on M7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2025 2025 Your RAP Journey -better together. 2 of 2 workshops held at AISSA. Aunty Elaine shared a Welcome to Country, and ??????
Note on J8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 Member schools invited to share their NRW activities on the website and the AISSA Linked In profile. 2024 Member schools invited to share their NRW activities on the website and the AISSA Linked In profile. Reply: 2025 Member schools invited to share their NRW activities in AISSA Reconciliation Newsletter and AISSA LinkedIn posts.
Note on I9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 05 29 AISSA staff and board members invited to hear Claire O'Connor SC, Barrister speak about her roles, cases she has been involved in and racism from her context. Reply: 2023 05 16 Staff invited to attend ADCSA event: Uluru Statement from the Heart; A Deepening Understanding with Noel Pearson at the Adelaide Town Hall. Reply: 2023 05 11 Staff attend the Hawke Centre Public lecture and Livestream: The Voice with Prof Tom Calma & Prof Dr. Marcia Langton. They will share their perspectives and experiences to explore why The Voice is needed and how it will potentially function. They will also address the common misinformation and hypotheticals that are consuming the media. Reply: 2024 KM attend St Johns Grammar School NRW Assembly with Governor of SA. Reply: 2023 KM Attend the NRW assembly at Immanuel Lutheran Primary. Reply: 2024 AD and AM attend Aboriginal Veterans SA Commemorative Service Reply: 2025 KS/DG attend Aboriginal Veterans SA Commemorative Service Reply: 2025 KS attend St Johns Grammar Reconciliation senior school assembly Reply: 2025 KS attend 2025 Lowitja O'Donoghue Oration Reply: 2025 18 AISSA staff attend NRW Reconciliation SA Breakfast Reply: 2025 AM attend Reconciliation SA Cultural Learning day at the State Library Reply: 2025 July. 15 AISSA staff attend Group Tour - Lowitja - A life of Leadership & Legacy
Note on J9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 06 03 AISSA staff invited to attend the NRW Charity screening of the film: The Last Daughter, hosted by Brenda Matthews.
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AISSA staff invited to attend 27-5-24 NRW Breakfast (at AISSA's table for 10) Reply: AISSA staff invited to attend 26-5-23 NRW Breakfast (at AISSA'S table for 10) Reply: 2024 AISSA staff invited to Reconciliation On The Road (Reconciliation SA event for NRW)
Note on I11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 05 17 AISSA staff record and sing: From Little Things, Big Things grow for NRW national video to be released in NRW.
Note on J11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2025 3/6 Whole staff cultural learning presented by Michele Oliphant. What allyship means to me. Working with communities in the NT and the work of AISSA. 2 hours Reply: 2025 Nunga Screen over 2 weeks, lunch time viewing.
Note on I12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 and 2024.KM registered events. Reply: 2025 KS registered events

## Relationship 1.3
Relationships
Sustained relationships built on respect, trust and integrity are foundational to engagement with Aboriginal and Torres Strait Islander Peoples. Strong relationships between Aboriginal and Torres Strait Islander Peoples and the AISSA are pivotal to being brave and advocating for truth telling and equity, as individuals and as an organisation. | [5 empty] | Review, Discuss, Act |  |  |  | Ongoing
Action | Responsibility | Timeline | Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
3. Promote reconciliation through our sphere of influence. | Chief Executive | June 2023 | Invite leaders of member schools, sector heads, the SACE, Reconciliation SA, politicians, and other stakeholders to the launch of the AISSA 2023-2026 Stretch RAP.
| Senior Reconciliation Consultant | May 2023, 2024, 2025 | Participate in quarterly RAP Leadership Gatherings
| Chief Executive and Senior Reconciliation Consultant | May 2025 | Implement strategies to engage all staff to drive reconciliation outcomes.
| Senior Reconciliation Consultant | October 2023, 2024, 2025 | Provide annual focus group opportunities to bring staff together in small groups to refelct on RAP progress.
| Senior Reconciliation Consultant | December 2023, m2024, 2025 | Invite staff from RWG to take leadership of RAP action deliverables through the allocation of the RWG roles.
| Chief Executive and RWG Communication Coordinator | October 2023, 2024, 2025. | Communicate our commitment to reconciliaiton publicly including, but not limited to, the AISSA Annual Report and the AISSA website | bar: Jan
| Chief Executive | September 2025 | Implement strategies to positively influence our external stakeholders to drive reconciliation outcomes.
| Chief Executive and Senior Reconciliation Consultant | January 2026 | Collaborate with 3 RAP and other like-minded organisations to implement ways to advance reconciliation.
| Senior Reconciliation Consultant | April 2023, 2024, 2025 | Lead the Australian Independent Schools/Independent Schools Association National Reconciliation Working Group to build a national commitment to reconciliation and advocate for ‘truth telling.’
| Chief Executive and Senior Reconciliation Consultant | January 2026 | Utilise our local, state and national spheres of influence to inspire our member schools to take braver action to address reconciliaiton.
| Senior Reconciliation Consultant | November 2023, 2024, 2026 | Regularly, at least 6 times a year, through a network email and the AISSA website, promote significant reconciliation days, events, resources, updates, programs and professional learning. | bar: Jan
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 19 Mar 2024 Member schools, sector heads, SACE, Rec SA, Ed Minister and stakeholders invited to launch held at Wine Centre
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 AIS Reconciliation Group meeting Reply: 2023 Reconciliation Industry Network Group meeting Reply: 2024 Reconciliation Industry Network Group meeting
Note on G5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2025 KS and MO attend the RING meeting and Reconciliation SA with Uncle Tamaru Kartinyeri Kaurna Language Workshop
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024, 2025 Reconciliation Industry Network Group meeting
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 AIS Reconciliation Group meeting Reply: 2023, 2024 2023 Reconciliation Industry Network Group meeting
Note on L5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 AIS Reconciliation Group meeting Reply: 2023, 2024 Reconciliation Industry Network Group meeting Reply: 2024 ISA/AIS Reconciliation leadership gathering in Canberra (KM)
Note on M5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024: KS attend ISA/AIS Reconciliation Leadership strand of the Staff Symposium at AISVIC
Note on O5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 AIS Reconciliation Group meeting Reply: 2023, 2024 Reconciliation Industry Network Group meeting Reply: 2024 KM to Canberra for a National RAP Leadership forum. Reply: 2024 KS attend ISA/AIS National Reconciliation leadership mtg.
Note on F6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 shared information about history of AISSA RAP journey and commitment to it.
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 RWG communication to all staff re action of delieverables
Note on N6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024: 1st staff reconciliation book club for AISSA staff
Note on O6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 All staff meeting AD & JT share Immersion Trip learning
Note on L7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 whole staff involvement small group feedback.
Note on N7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024. KM share to RWG focus group data. RWG begin action plan phase
Note on O7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024: AD/KS present focus group data and RWG action plan to all AISSA staff at staff meeting.
Note on P7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024: Following each RWG meeting a newsletter is shared to all AISSA staff re RAP updates
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Ongoing all year: reminders to RWG members to update RAP calendar and Activity Tracker.
Note on P8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024: staff roles and responsibilities reviewed and re-allocation made as per need. All groups share updates at each RWG. Put in place procedures to ensure all events, roles etc are planned and accountabilities in place. This includes the RAP calendar.
Note on J9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6 June 2024 AISSA AGM - Chair's Report to all members affirms RAP commitment
Note on N9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023. 2024, 2025: Via LinkedIn posts throughout the year.
Note on P9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023. 2024: Via LinkedIn posts throughout the year.
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024: KS meet with Aunty Elaine to begin relationship with her and begin to plan for 2025.
Note on M10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024: KS meet with Jade Brook to begin a relationship and discuss ideas for 2025.
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 5 Apr AD attended Reconciliation SA's Launch of Education, Action, and Change: an anti-racism resource for schools and preschools & shared resources with AISSA staff and posted on LinkedIn
Note on P11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024: Further develop intentional partnership with Australian Together that has included the provision of cultural training of our AISSA staff. AISSA actively promoted A.T through communications and PL with schools. 2023, 2024: Further partnership with Culture College in the offering of the Immersion Trip to our member schools. 2023, 2024: Reconciliation SA - active collaboration.
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 KM leads the AIS/ISA Reconciliation group Reply: 2025 KS joins group after KM leaves.
Note on J12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 KM leads the AIS/ISA Reconciliation group
Note on L12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 KM leads the AIS/ISA Reconciliation group
Note on M12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KS attend ISA/Ais Staff Symposium to discuss reconciliation, share resources, direction etc.
Note on O12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 KM leads the AIS/ISA Reconciliation group Reply: From November 2024: KS participates in the National Reconciliation Working Group.
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ensure ongoing representation at ISA level for RAP and Cultural Awareness from AISSA staff
Note on G13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024: Invite member schools, politicians, other sectors to our Stretch RAP Launch to hear our vision and commitment to reconciliation.
Note on P13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024: Via LinkedIn re-posting reconciliation events, posts, perspectives under the banner of our organisation throughout the year.
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 create LinkedIn strategy.
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 newsletter sent
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 newsletter sent
Note on I14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 05 20. AISSA Project. 10 member school teams + students from each school. Year 3 of 3. Innovative Models of Learning Recognition Project: Creative Seminar 2. The seminar will provide the opportunity to work with Michael Bunce, Charlie Leadbeater and Tony Mackay face-to-face as well as leading academics from Flinders University. Sharing with us will also be Renee Watego (Contemporary Artist, Bundjalung decent with Kin ties to the Torres Strait Islands and South Sea Islands), Bronwyn Lee (CEO at Learning Creates Australia) and Hayley McQuire (Darumbal and South Sea Islander woman; Co-Chair Learning Creates Australia). The emphasis of the day will be on the key themes of narration and representation of learning. This focus will support our aim to broaden the ways education systems can value and recognise learning and achievements that are not only part of a standardised western system. A focus on Aboriginal and Torres Strait Islander ways of knowing and being, translated into ways to narrate and illustrate learning. Student workshops and voice. Teacher/leader workshops. Students feedback to whole group and panel of leaders. (see MH/KS for details)
Note on K14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 newsletter sent
Note on N14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 newsletter sent
Note on O14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 Newsletter communication

## Relationships 1.4
Relationships
Sustained relationships built on respect, trust and integrity are foundational to engagement with Aboriginal and Torres Strait Islander Peoples. Strong relationships between Aboriginal and Torres Strait Islander Peoples and the AISSA are pivotal to being brave and advocating for truth telling and equity, as individuals and as an organisation. | [5 empty] | Review, Discuss, Act |  |  |  | Ongoing
Action | Responsibility | Timeline | Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
4. Promote positive race relations through anti-discrimination strategies. | Chief Executive and Head of Workplace and Human Relations | November 2023, 2024, 2025 | Engage with Aboriginal and Torres Strait Islander staff and Aboriginal and Torres Strait Islander advisors to continuously improve our anti-discrimination policy. NB - Policy is called Bullying, Discrimination, Equal Opportunity and Harassment Policy | Ongoing Oct: 2025
| Chief Executive and Head of Workplace and Human Relations | January 2024, 2025, 2026 | Communicate and implement our improved anti-discrimination policy for our organisation. | Jan: 2026
| Head of Workplace and Human Relations | November 2023, 2024, 2025 | Continuously refine and improve HR policies and procedures concerned with anti-discrimination.
| RWG Cultural Learning Coordinators | August 2023, 2024, 2025 | Provide information to senior leaders and staff about countering racism, and additionally, undertake this as an intentional focus of staff cultural learning for one year of our RAP.
| Chief Executive | January 2026 | Senior leaders to publicly support anti-discrimination campaigns and initiatives against racism.
Note on N4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Policy last updated Oct 2023. Due for review Oct 2025 - must consult
Note on L6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cultural Awareness Induction Policy due for review May 2026, ATSI Employment, Development & Retention Policy due for review August 2025
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 5 Apr AD attended Reconciliation SA's Launch of Education, Action, and Change: an anti-racism resource for schools and preschools & shared resources with AISSA staff and posted on LinkedIn
Note on L7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024: It’s a RAP PL for schools; share the anti-racism document and resources with attendees and staff at AISSA.
Note on P7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cultural training for AISSA Staff throughout the year, led by Aboriginal and Torres Strait Islander people.
Note on H8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 5 Apr AD attended Reconciliation SA's Launch of Education, Action, and Change: an anti-racism resource for schools and preschools & shared resources with AISSA staff and posted on LinkedIn
Note on O8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 KS attend the 2-day National RAP Conference in Brisbane.

## Relationships 1.5
Relationships
Sustained relationships built on respect, trust and integrity are foundational to engagement with Aboriginal and Torres Strait Islander Peoples. Strong relationships between Aboriginal and Torres Strait Islander Peoples and the AISSA are pivotal to being brave and advocating for truth telling and equity, as individuals and as an organisation. | [5 empty] | Review, Discuss, Act |  |  |  | Ongoing
Action | Responsibility | Timeline | Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
5. Actively promote Reconciliation Australia's Narragunnawali: Reconcilitation in Education programs to member schools. | Senior Reconciliation Consultant | December 2023, 2024, 2025 | Partner with Reconciliation SA and local Elders to support Leaders, RAP coordinators and educators to further develop strategies to deepen the implementation of their RAPs via the Narragunnawali and Reconciliation SA professional learning workshops. | bar: Jan
| Senior Reconciliation Consultant | December 2023, 2024, 2025 | Continue to promote Reconciliation Australia’s Reconciliation in Education program to all member schools. | bar: Jan
| Senior Reconciliation Consultant | December 2023, 2024, 2025 | Support member schools using the processes from the Narragunnawali platform to publish and refresh their RAPS on an annual basis. | bar: Jan
| Senior Reconciliation Consultant | May 2023, 2025 | Encourage member schools who have shown outstanding commitment to reconciliation to apply for the Narragunnawali Awards 2023 and 2025.
| Senior Reconciliation Consultant | March 2024 | Establish an invitation to join a Community of Learners group, focussed on addressing key actions from the Narragunnawali’s platform, using a variety of communication channels to be inclusive of all local and regional member schools.
| Chief Executive | November 2023, 2025 | Invite annually, one Junior school and one Combined or Secondary Principal to address their peers at a formal AISSA meeting to share their school's reconciliation journey, through the lens of Narragunnawali RAP.
| Chief Executive | November 2023, 2024, 2025 | Establish an award that recongnises the work of a staff member or members from our member schools who has championed the Narragunnawali RAP in their school. This prize will be preesented at the annual AISSA Appreciation Function.
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 KM meet with individual schools to support their RAP journeys.
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 KM meet Natalie Gentle to discuss the promotion of schools to apply for the Narragunawali Awards.
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 AISSA PL It’s a RAP with Elders and school leaders to implement and deepen RAP journeys
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024: AISSA PL It’s a RAP with Elders and school leaders to implement and deepen RAP journeys
Note on O4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DG to provide a 2 hour online session for member schools - Designing Purposeful Tasks Using the AC v9 Cross Curriculum Priority ATSI Histories and Perspectives
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 KM to promote Reconciliation Australia's Education program as a integral resource for schools to utilize.
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024: Intentional promotion of resources to support NRW.
Note on L5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024: at all of our PL we promote this resource.
Note on O5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 KS attend meeting at Reconciliation SA with CE and other leaders in SA. The purpose of the gathering - To unite leaders on a common purpose to discuss options to strengthen the Reconciliation movement in South Australia. Proposed Agenda Highlights of the conference Issues and challenges in SA Strategic options for 2025 – 2026 Reply: 2024 KS attend Reconciliation and Education: Past-Present-Future education jurisdictions (de)briefing session. Teams Meeting Following the release of the summary report and key recommendations from the Reconciliation and Education: Past-Present-Future Forum, this meeting will convene key representatives from education jurisdictions to collaborative reflect on the recommendations and discuss potential next steps together in the important work of reconciliation and education. Addressing the recommendations of the Forum will require a collaborative, relational, and coordinated response from all of us within the sector
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 ongoing support to member schools to refresh and publish RAP.
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2025 Part 1 or a 2-part series: Your RAP Journey PL in partnership with Reconciliation SA
Note on N6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024: Reminder comms to remind schools to reflect on their RAP status.
Note on O6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 KS attend St Johns Grammar community event to share new RAP and receive community feedback.
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2025 Ks contacted 3 schools specifically; and shared generally to all member schools via email and newsletter
Note on J8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 Learning Community Cultural Gathering held at Tatachilla Lutheran College Eco Classroom. Focus for Southern region AISSA member schools. KM and Uncle Tamaru attended.
Note on L8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2025 KS attend the St Johns Grammar community information session for school RAP
Note on O8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 KS attend the St Johns Grammar community information session for new RAP
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Anne Dunstan: RAP Launch 2024 - examples of Narragunnawali RAP actions in member schools shared visually and verbally
Note on O9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Secondary/Combined Heads Networking focus on RAP journeys
Note on P9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Primary Heads Networking focus on RAP journeys
Note on O10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Anne Dunstan: Aunty Elaine Magias was awarded Noel Volk 2023 Reply: Sharon Lynch, Immanuel Primary School was awarded a Noel Volk for her work leading the School's RAP

## Respect
Respect | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15
We advocate that Aboriginal and Torres Strait Islanders’ histories and cultures, past, present and future, are fundamental to our very understanding of what makes Australia unique in the world, and promote constitutional change that recognises that their sovereignty was never ceded. Our work both, both internal and external, is strongly guided by our commitment to increasiing cultural learning that prioritises truth telling and our deep reflection upon our own hsitory as well as the history of First Nations Peoples through guided, respectful learning opportuinities informed by our partnerships with Kaurna Elders. We will embed this thoughout the year utilising our partnerships and sphere of influence.
Action | Responsibility | Timeline | Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
6. Increase understanding, value and recognition of Aboriginal and Torres Strait Islander cultures, histories, knowledge and rights through cultural learning. | Senior Reconciliation Consultant | August 2024 | Conduct a review of cultural learning needs within our organisation.
| Senior Reconciliation Consultant and RWG Cultural Learning Coordinators | October 2023, 2024, 2025 | Consult local Traditional Owners and/or Aboriginal and Torres Strait Islander advisors on the implementation of a cultural learning strategy.
| Senior Reconciliation Consultant and RWG Cultural Learning Coordinators | November 2023, 2024, 2025 | Implement and communicate a cultural learning strategy for our staff.
| Chief Executive | January 2024, 2025, 2026 | Commit all RAP Working Group members, HR managers, senior executive group and all staff to undertake formal and structured cultural learning.
| Chief Executive | March 2023, 2024, 2025 | All staff undertake face to face formal and structured cultural learning.
7. Promote First Nations perspectives and culturally inclusive pedagogies across the curriculum. | Head of Educational Services | July 2024, 2025 | Lead our member schools to embed First Nations histories, cultures and perspectives utlising culturally responsive pedagogy.
| Head of Educational Services | May 2023, 2024, 2025 | Continue to be proactive in collaborating with ACARA, ACEQUA, SACE and AITSL to embed First Nations perspectives and culturally inclusive pedagogies across the curriculum.
| Head of Educational Services | November 2023, 2024 | Deliver a series of professional learning workshops that focus on the Australian Curriculum v 9.0 Science and Mathematics, that build teacher capacity to include the Aboriginal and Torres Strait Islander elaborations in their teaching and learning.
| Head of Educational Services | November 2023, 2025 | Deliver a series of professional learning workshops that focus on the Australian Curriculum v 9.0 and build teacher capacity to include the Aboriginal and Torres Strait Islander elaborations in their teaching and learning.
| Senior Reconciliation Consultant | November 2024 | Support schools to provide forums for students to offer perspectives that progress a culturally responsive environment.
8. Demonstrate respect to Aboriginal and Torres Strait Islander peoples by observing cultural protocols. | RWG Cultural Learning Coordinator | March 2023, 2024, 2025 | Deepen the staff's understanding of the purpose and significance behind cultural protocols, including Acknowledgement of Country, Smoking Ceremony and Welcome to Country, by listening with respect and reflecting on the narrative that accompanies each protocol.
| RWG Cultural Learning Coordinator | July 2023, 2024, 2025 | Update and communicate a cultural protocol document (tailored for all local communities we operate in), including protocols for Welcome to Country, Smoking Ceremony and Acknowledgement of Country.
| Senior Reconciliation Consultant | December 2023, 2024, 2025 | Invite a local Traditional Owner of Custodian to provide a Welcome to Country or other appropriate cultural protocol at 6 significant events each year, including Cultural learning Workshops, NRW and tha Launch of the AISSA 2023-2026 RAP.
| Chief Executive | December 2023, 2024, 2025 | Include and Acknowledgement of Country or other appropriate protocols at the commencement of important meetings.
| Chief Executive | December 2023, 2024, 2025 | Staff and senior leaders provide an Acknowledgement of Country or other appropriate protocols at all public events.
| Chief Executive | 2023-06-01 00:00:00 | Update the digital Acknowledgment of Country display in the AISSA Reception area to reflect the AISSA RAP 2023-2026.
Action | Responsibility | Timeline | Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
9. Engage with Aboriginal and Torres Strait Islander cultures and histories by celebrating NAIDOC Week. | RWG Events Coordinators | First week in July 2023, 2024, 2025 | RAP Working Group to participate in an external NAIDOC Week event.
| Head of Workplace and Human Relations | November 2023, 2024, 2025 | Review HR policies and procedures to remove barriers to staff participating in NAIDOC Week.
| RWG Cultural Learning Coordinators | First week in July 2023, 2024, 2025 | Support all staff to participate in 2 NAIDOC Week events in our local area.
| RWG Events Coordinators | First week in July 2023, 2024, 2025 | Organise an internal NAIDOC Week event for the AISSA staff annually.

## Opportunities
Opportunities
We support Aborigianl and Torres Strait Islander popele and businesses through our commitment to developing mutually beneficial opportunities. This will be done by ensuring we are addressing opportunities for employment of staff, embedding procurement processes and investing in partnerships where Aboriginal and Torres Strait Islander peoples and communities benefit.
Action | Responsibility | Timeline | Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
10. Improve employment outcomes by increasing Aboriginal and Torres Strait Islander recruitment, retention and professional development. | Chief Executive | August 2023, 2024, 2025 | Engage with Aboriginal and Torres Strait Islander staff to consult on our recruitment, retention and professional development strategy. NB Policy called Aboriginal and Torres Strait Islander Employment, Development and Retention Policy
| Chief Executive and Head of Workplace and Human Relations | November 2023, 2024, 2025 | Review and update an Aboriginal and Torres Strait Islander recruitment, retention and professional development strategy. | Nov: 2025
| Chief Executive | August 2023, 2024, 2025 | Advertise job vacancies to effectively reach Aboriginal and Torres Strait Islander stakeholders. | bar: Jan
| Chief Executive and Head of Workplace and Human Relations | November 2023, 2024, 2025 | Review HR and recruitment procedures and policies to remove barriers to Aboriginal and Torres Strait Islander participation in our workplace. | Nov: 2025
| Chief Executive | 2025-12-01 | Aboriginal and Torres Strait Islander persons to be engaged as a senior policy level in the organisation.
| Chief Executive | December 2023 | Mentor and financially support Aboriginal and Torres Strait Islander employees to engage in professional learning that includes opportunities to participate in tertiary education.
| Chief Executive | December 2025 | Use every endeavour to increase by 100% the number of Aboriginal and Torres Strait Islanders employed by the AISSA. | bar: Jan
| Chief Executive and Head of Workplace and Human Relations | October 2025 | Further develop strategies to ensure we are a culturally safe workplace and an employer of choice for First Nations Peoples.
| Chief Executive and Head of Workplace and Human Relations | October 2025 | Develop and implement a strategy to provide work experience for Aboriginal and Torres Strait Peoples. | Oct: 2025
| Indigenous Secondary School Mentor | November 2023, 2024 | Continue to provide mentoring for secondary Aboriginal and Torres Strait Islander students. | bar: Feb
11. Increase Aboriginal and Torres Strait Island supplier diversity to support improved economic and social outcomes. | Chief Executive | November 2023, 2024, 2025 | Continue to implement and refine an Aboriginal and Torres Strait Islander procurement strategy.
| Chief Executive | November 2023, 2024, 2025 | Continue to utilise Supply Nation members so we can support as many businesses as possible. | bar: Jan
| Chief Executive | November 2023, 2024, 2025 | Develop and communicate opportunities for procurement of goods and services from Aboriginal and Torres Strait Islander businesses to staff.
Action | Responsibility | Timeline | Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Chief Executive | November 2023, 2024, 2025 | Continue to review and update procurement practices to remove barriers to procuring goods and services from Aboriginal and Torres Strait Islander businesses.
| Chief Executive | December 2025 | Maintain 10 commercial relationships with Aboriginal and/or Torres Strait Islander businesses. | Dec: 2025
| Chief Executive | November 2023, 2024, 2025 | Ensure an annual procurement of $35,000 from Aboriginal and Torres Strait Islander businesses.
| Chief Financial Officer | November 2023, 2024, 2025 | Teach all relevant staff the processes involved in contracting Aboriginal and Torres Strait Islander businesses through Supply Nation or an equivalent organisation.
12. Continue to provide economic support to remote First Nations' communities. | Chief Executive | August 2023, 2024, 2025 | Continue to financially support a minimum of two AISSA staff members to experience the Culture College Immersion Program in East Arnhem Land annually. | bar: Jan
| Chief Executive and Senior Reconciliation Consultant | August 2023, 2024, 2025 | Increase the number of member schools who participate in the annual Culture College Immersion Program in East Arnhem Land.
| Chief Executive and Senior Reconciliation Consultant | August 2025 | Extend the participation of the Culture College Immersion Program in East Arnhem Land, to include the Associations of Independent Schools by promoting it to all states and territories.
| Senior Reconciliation Consultant | August 2025 | Develop and implement in partnership with Culture College, local Elders and the Yolngu community, an immersion program for member schools that provides a ‘Homeland’ experience in situ.
13. Continue to promote cultural safety and comptency both internally and externally. | Senior Reconciliation Consultant | May 2023, 2024, 2025 | Continue our commitment to First Nations student voice through a range of mechanisms which support the cultural safety of those involved, is purposeful and draws from a range of modes and opportunities. | bar: Feb
| Head of Educational Sevices | December 2023, 2024, 2025 | Provide annual face to face professional learning for the AISSA Education Team on cultural competency, in line with the AITSL Final Report June 2022 on 'Building a culturally responsive Australian teaching workforce.' | bar: Jan
| Senior Reconciliation Consultant | December 2023, 2024, 2025 | Provide 3 professional learning opportunites annually, focussing on creating culturally safe classrooms for member schools in partnership with First Nations' advisors.
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Policy ratified Aug 2022 due for review August 2025
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Three vacancies posted on Indigenous Employment Australia website (March 2025)
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Snr Mngr position advertised via iWork Jobsite (May 2024)
Note on L6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CRRE Consultant vacancy advertised via atsijobs.com.au
Note on O6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Marketing & Communication Project Officer vacancy advertised via atsijobs.com.au
Note on P8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: E.g. Contract for Services review 2024 w GS and SB
Note on M9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 SB supported to complete Aust Boarding Schools Association PL
Note on N9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Developing coaching/mentor support approach w First Nations mentor
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Anne Dunstan: Consultative response to 26 January discussions raised by 2 members of staff in 2024. Change to terminology from Australia Day to 26 January.
Note on N12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Anne Dunstan: Consider opportunity to tie with a member school's WE program
Note on F13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 - 2024 SB. Scholarship application from discussion to application. Reply: 2023 - on going. SB helping Mentees with resumes and work experience. Applying for jobs. Reply: Welcoming new students into the Mentoring Program. Reply: 2023- 2024 Implementation of school Newsletter Reply: Indigenous Forum to share and connect with other member schools
Note on H13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recently supported a student at the University of Adelaide on their recent camp.
Note on I13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reengaged with Tatachilla and back to supporting FN students after a year off. Reply: Gained two new schools to add to the data.
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Anne Dunstan: 2024 Engaged with Ngiilay Gift Boxes to provide free advertising via AISSA channels
Note on O14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Refine Contract for Services template (inc Procedure) for more inclusive practice SB & GS
Note on F16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 RWG Communication Coordinators published and shared newsletter with AISSA staff.
Note on O18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Refine Contract for Services template (inc Procedure) for more inclusive practice SB & GS
Note on P21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Refine Contract for Services template (inc Procedure) for more inclusive practice SB & GS and disseminate to staff
Note on L23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 Consistent numbers, school diversity re attendance and participation.
Note on N23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Yongu Elder Djapirri invited to meet with member schools at AISSA
Note on L24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 AISWA attendance
Note on P24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024, 2025: Information about the Immersion trip is shared twice a year with the AIS network. An invitation is extended to attend.
Note on L25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024, 2025: AISSA Immersion trip.
Note on P25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024, 2025: Immersion trip planned and implemented.
Note on F26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 An embedded focus in AISSA's professional learning program.
Note on G26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Student representation at the AISSA Stretch RAP. 2023 SB/KM following dialogue around students cultural safety; intentional strategies to support cultural safety. This is promoted through the school's RAP working groups.
Note on P26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024, 2025: Opportunity for schools to further explore and develop students voice. Supported by 3 x PL Culturally Safe Classrooms and Schools.
Note on P27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Part of ongoing commitment to whole staff cultural learning
Note on I28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 Workshop 1 of the series
Note on L28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 workshop 2 of the series
Note on N28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024 workshop 3 of the series
Note on P28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023, 2024, 2025: Opportunity for schools to further explore culturally safe environments for member schools by 3 x PL Culturally Safe Classrooms and Schools.

## Governance
Governance
Action | Responsibility | Timeline | Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
14. Establish and maintain an effective RAP Working Group (RWG) to drive governance of the RAP. | Chief Executive | January 2024, 2025, 2026 | Maintain Aboriginal and Torres Strait Islander representation on the RWG. | bar: Jan
| RWG Chair | June 2023, 2024, 2025 | Maintain a Terms of Reference for the RWG.
| Chief Executive | January, May, August and November 2023, 2024,2025 | Meet at least four times per year to drive and monitor RAP implementation.
| Chief Executive | August 2023, 2024, 2025 | Annually extend an invitation to all members of the AISSA staff to join the RWG.
| RWG Chair | November 2023, 2024, 2025 | Annually review the roles and responsibilities of the RAP RWG to ensure a dispersed leadership model and that the roles are aligned to the RAP implementation.
15. Provide appropriate support for effective implementation of RAP commitments. | Chief Executive | August 2023, 2024, 2025 | Embed resource needs for RAP implementation.
| Chief Executive | November 2023, 2024, 2025 | Continue to embed key RAP actions in performance expectations of senior management and all staff. | bar: Jan
| Chief Executive and RWG Chair | June 2023, 2024, 2025 | Continue to embed appropriate systems and capability to track, measure and report on RAP commitments.
| Chief Executive | June 2023, 2024, 2025 | Maintain an internal RAP Champion from senior management. | bar: Jan
| Chief Executive | June 2023, 2024, 2025 | Include our RAP as a standing agenda item at senior management meetings. | bar: Jan
16. Build accountability and transparency through reporting RAP achievements, challenges and learnings both internally and externally. | Senior Reconciliation Consultant | June annually | Contact Reconciliation Australia to verify that our primary and secondary contact details are up to date, to ensure we do not miss out on important RAP correspondence.
| Chief Executive | 1 August annually | Contact Recnociliation Australia to request our unique link, to access the online RAP Impact Questionnaire.
| Chief Executive and Senior Reconciliation Consultant | 30 September 2023, 2024, 2025 | Complete and submit the annual RAP Impact Measurement Questionnaire to Reconciliation Australia.
| RWG Communications Coordinator | March, May, August, November 2023, 2024, 2025 | Report RAP progress to all staff and senior leaders quarterly.
| Chief Executive | December 2023, 2024, 2025 | Publicly report against our RAP commitments annually, outlining achievements, challenges and learnings.
| Chief Executive | April 2024 | Continue to participate in Reconciliation Australia’s biennial Workplace RAP Barometer.
| Senior Reconciliation Consultant | 2026-05-01 | Submit a traffic light report to Reconciliation Australia at the conclusion of this RAP | Apr: 2026
17. Continue our reconciliation journey by developing our next RAP. | Chief Executive and Senior Reconciliation Consultant | September 2025 | Register via Reconciliation Australia's website to begin developing our next RAP. | Sep: 2025
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 RWG meeting 2024 RWG meeting
Note on F6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Feb meeting
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 March 2 meetings
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 May meeting Reply: 2024 May meeting
Note on L6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 Aug meeting Reply: 2024 Aug meeting
Note on N6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Oct meeting
Note on O6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 Nov meeting
Note on P6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 Dec additional meeting
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Invitation sent Feb each year w a reminder in first staff meeting each yr
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 RWG meeting to include new members. Review of roles is shared first by current members. Reply: 2023 RWG meeting to include new members.
Note on N9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Reconciliation Budget set
Note on G11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Senior Reconciliation Consultant and RWG Chair developed the 2023-2026 Stretch RAP Activity Tracker. Document shared via email and at the May RWG meeting with the team. Team responsibility to insert comment/activity.
Note on I11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 05 10 RAP Calendar resource created. This calendar is to be 'invited' to any RAP deliverable activities eg. Stakeholders Morning Tea, RWG Breakfast, Policy updates, meetings. Goal is to have an archive of all deliverables over a calendar year.
Note on E12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Currently CE
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Termly Executive Meetings
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2025: KS contact details updated via email.
Note on J14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023
Note on N14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024: KM to update as she meets/communicates including KS in these.
Note on M15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 & 2024 Completed
Note on M16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 complete
Note on F17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2025 Term 1 Staff Update 27/02/25
Note on G17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Term 1 Staff Update sent 18/03/24
Note on I17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Term 2 Staff Update sent 31.05/24
Note on M17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Term 3 Staff Update sent 17/09/24
Note on P17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024, 2025: RAP progress shared with all AISSA staff via a RWG newsletter which is shared quarterly after each RWG meeting. Reply: 2024 Term 4 Staff Update sent 11/12/24
Note on J18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2024 Chair's Report AGM identifies RAP progress
Note on L19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2023 & 2024 Barometer completed

## TrackingProgress
Tracking progress and reporting
Action | Responsibility | Timeline | Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec